Working paper (to be updated by TT-GISC-2018)

Background

Following table was updated by TT-GISC-2016 in Brasilia, 18-22 April 2016

TT-GISC-2017 (Nov, 2017) agreed to take over the action items

Action required

Participants are requested to review the TT-GISC Action Items and to update status of each action.

TT-GISC Action Items

| Action Number | Decision/recommendation/ action | Responsible | Objective/deadline | Status To be updated As of Sep 2018 |
| --- | --- | --- | --- | --- |
| 14/1-2 | Action: a) Encouraged all GISCs to start to utilize the competency and learning guide in their capacity development and training activities. b) All GISCs should aim at ensuring centres in their area of responsibility have staff equipped with appropriate competencies and thus maximize their ability to support and benefit from WIS | GISCs | Leave on agenda | Ongoing, especially now we have MoW as per 14/1-1 |
| 14/1-11 | Action: Agreed to use the ET-WISC internal forum (http://www.wmo.int/pages/prog/www/WIS/wiswiki/tiki-view_forum.php?forumId=12) to discuss issues. | TT-GISC | Leave on agenda | Forum created, now need relevant usage. Ongoing |
| 14/1-12 | Action: a) Requested ET-CTS, while investigating cloud computing solutions, to address: legal issues of countries using storage outside of nation; - political barriers to one country using a service managed by another; and data access policy. b) The chair suggested that once ET-CTS has considered this document from a CTS perspective, it is recommended that at least a couple of GISCs experiment further with this concept. c) TT-GISC members to participate in Cloud project | a) ET-CTS chair, b) TT-GISC chair. c) Participating GISCs | a) March 2014 b) When convenient c) report back to next TT-GISC meeting | a) & b) both Done – Cloud project in progress c) new Project to report back to TT-GISC2017 with aim to have implementation of an operational service starting in mid-2018 |
| 14/1-13 | Recommendation: Agreed that detailed monitoring would be at the GISC level, while only the common holding needs to be monitored globally. Thus all GISCs should meet the basic requirement set by monitoring a) The number of core Cache updates in the last 24 hours and b) 24 hour input volume and c) number of items in the complete cache, plus the status of the common holding (core) component. Each GISC is encouraged to establish more detailed monitoring for its own quality assurance process. (See also action 14/1-3) d) TT-GISC maintain close liaison with monitoring team | Remy as project lead and Yasu as technical lead. Participating GISCs project focal points | As per action 14/1-3 Leave on agenda | As per action 14/1-3 current project with Remy as project lead and Yasu as technical lead and to report back to TT-GISC. |
| 14/1-14 | Action: Agreed to: a) the need for GISC agreement making processes necessary to manage multilateral GISC issues. b) establish a sub team to define TOR and working practices to report back to TT-GISC on recommended procedures for approving inclusion of data in GISC core cache, and similar decisions, so it can be reported to ET-WISC and ICT-ISS. c) need to provide TT-GISC and TT-DC opinions to ITT-WIS | Japan(lead), USA, Germany, France, UK, Russian Fed and Chair TT-DC | June 2014 CBS requested ICT-ISS establish ITT-WIS to look at governance. Leave on agenda | a&b Done – underway Note new part C added in 2015 meeting. |
| 14/1-15 | Action: Meeting a) confirmed file format of 24h cache to be full meteorological bulletin as in report of ET-WISC meeting, 2013. b) encouraged all GISCs to use the full “Meteorological bulletin” as default representation of GTS-bulletin data instances | GISCs | ASAP Leave on agenda | Done – Ongoing but chair wants to leave on agenda for 24 hr cache item TT-GISC still has some concerns on this issue |
| 14/1-16 | Action: Establish a method by which access to a GISC cache is reviewed/audited. | Germany, France,UK (lead),and Japan | Next TT-GISC meeting Leave on agenda | Consider under WIS monitoring item Noted new WMO_DistirbutionScopeCode addresses cache holding. In addition CMA paper on monitoring Cache (Doc35) to be passed to Monitoring Team |
| 14/1-17 | Action: TT-GISC recommended: a) GISCs should agree on a single standard to facilitate user federation; b) Establish group to investigate, including establishing basic use cases c) Confirm elements needed to be shared. | USA, Germany, France (Lead), Japan, China,, Australia, UK | Report back to TT-GISC by 2015 (prior Cg 17) 20162017 | No report for this meeting so still To be done New opportunity under eduGain project. |
| 14/1-20 | Recommendation: TT-GISC a) agreed that GISC working arrangements, including recommended practices from TT-GISC, should be recorded in an easily maintained Operations Guide to GISCs (possibly a wiki) b) proposed that Appendix D, Annex to 9.2 should be included in a GISC operating guide. | TT-GISC | Chair add (a) to action plan prior to next meeting | (a) Wiki part not done. Page set up as http://wis.wmo.int/pages=TT-GISC-ops (b) completed. See WIS guide updates in CBS report. Leave (a) on agenda |
| 14/1-21 | Recommendation: TT-GISC recommends that WMO be registered as a DCPC with a principal GISC of Toulouse. | Secretariat and ET-WISC. | Leave on agenda | CBS approved, Meteo-France agreed to be Principal GISC, WMO still working out internal processes through Library |
| 14/1-22 | Action: TT-GISC: a) Agreed that there was a need for a standard format and method along the lines proposed by GISC Pretoria and described in Appendix D, Annex to 9.4. b) Requested France and Germany to explore this issue further to prepare a report to TT-GISC with an aim to including the details in the GISC Practices Guide | France and Germany | June 2014 Leave on agenda | ICT-ISS reviewed the form and recommendations of the TT-GISC and they asked that it be generalized. DWD has established outage service notice. DWD to provide to chair who will circulate to TT-GISC, then ET-WISC for comment. |
| 15/1-1 | Requested GISCs that were unable to report to TT-GISC 2015, to still provide status reports | Jeddah, New Delhi, and Tehran. | ASAP | Requests sent but no result. Leave on agenda for missing reports from 2016 meeting. |
| 15/1-2 | Noting closure of 14/1-10 and Doc(xx) from DWD. Request DWD to clarify what still needs to be done regarding OAI timestamps. | DWD (Markus & Bernd) | Before next meeting of TT-GISC | Markus clarified the need. Leave on agenda |
| 15/1-3 | Add CBS-16 demo to WIS monitoring team. | Yasu | Before next meeting of TT-GISC | Done, Changes locked in, project under way as requested. |
| 15/1-4 | Provide information to Secretariat in order to populate and update GISC Backup Table (Working Doc 07) relating to GISC data collection and distribution in their AoR. | GISCs / Secretariat | Before next meeting of TT-GISC | Done, table updated at this meeting. Need to put on GISC operations wiki page Leave on agenda |
| 15/1-5 | Cache variability - GISCs to review analysis of cache variation - CMA to upload excel spreadsheets containing the number and size of TTAAii and CCCC files in the cache used for cache analysis to meeting page to facilitate GISCs analysis of cache variability. - All GISCs are encourage to submit data for future analyses. - Pass Doc 35 on cache monitoring to monitoring team. | a&c) GISCs b) CMA | a) Done b) and d- ASAP c) when next analysis occurs. | Leave on agenda |
| 15/1-6 | GISCs to investigate and if possible implement new data policy categories to account for NoLimitation, including treatment of empty policy field. See http://wis.smo.int/page=ManualWIS 19 May 2015 reflecting CBS fast track approval of WIS Metadata. | GISCs | GISCs to report back on issues and status at next meeting | Not done, Leave on agenda |
| 15/1-7 | a) GISCs to investigate and if possible implement WMO_DistributionScopeCode - Implement code - Encouraged GISCs to review in consultation with data providers existing metadata to include the globalavailable, cache or regional or source flag and batch update metadata. b) Chair to adivise CBS through ET-WISC/ICT-ISS of the urgent need for ITT-WIS to provide guidance | a) GISCs b) Chair | a) GISCs to report back on issues and status at next meeting b) ASAP | a) Not done, b) Done, to be addressed at EC-68 Leave on agenda |
| 15/1-8 | Investigate inclusion of regional networks on dynamic WIS monitoring diagram using information in existing JSON files. | Jose | Through monitoring Team, report back to next TT-GISC | Leave on agenda |
| 15/1-9 | GISCs are to investigate if they are able to generate Vol C1 or if work is being done within their organization | GISCs | GISCs to report back on issues and status at next meeting | Meeting reported no change on issue other than JMA and others are working in IPET MDRD (see TT-ApMD-2-FinalReportr.doc) Leave on agenda |
| 15/1-10 | GISCs should implement a training environment along the lines in WDoc3r1. | GISCs | GISCs to report back on issues and status at next meeting | Leave on agenda |
| 15/1-11 | a) Ask Monitoring Team to maintain pilot for GISCs to monitor and to investigate inclusion of some NCs. b) All GISCs are encouraged to 1) provide JSON files, and encouraged to include some NC/DCPC data. b) monitor the three WIS Common Dashboards. | GISCs | Monitoring team and GISCs to report back on issues and status at next meeting | Partially included in CBS Demo, Leave on agenda |
| 15/1-12 | meeting will forward the request described in Doc14 to IPET-MDRD | Chair | ASAP | Done, close issue |
| 15/1-13 | Review DBNet guide for sat programme. | all | Done | Close item |

| TT-GISC Action Number | Decision/recommendation/ action | Responsible | Objective / deadline | Status To be updated As of Sep 2018 |
| --- | --- | --- | --- | --- |
| 16/1-1 | Recommendation: TT-GISC noting that aside from the twice yearly monitoring survey and annual corporate survey, there are many other surveys making their way to GISC staff. It asked the secretariat to try and coordinate these additional surveys to minimise work on staff. | Secretariat | Ongoing |  |
| 16/1-2 | Action: GISCs should change their GEOSS SRU server pointers from http://clearinghouse.cisc.gmu.edu/geonetwork/srv/en/portal.sru? to http://gisc.kma.go.kr/openwis-user-portal/srv/en/main.home/portal.sru?. | GISCs | CBS-16 |  |
| 16/1-3 | Action: GISCs to use template for future GISC reports provided in Annex 5. All GISCs to provide their reports, even when unable to attend TT-GISC meetings | GISCs | TT-GISC2017 |  |
| 16/1-4 | Action: All GISCs to: a) liaise with DWD to create their accounts and to make internal arrangements so that process works during backup mode. b) make accounts with Moscow and Tokyo who are running the same service. | GISCs | CBS-16 |  |
| 16/1-5 | Action: GISCs to advise TT-GISC of: a) their back up arrangements based on the spread sheet so GISCs can follow up; b) add this to the TT-GISC wiki GISC Ops page (http://wis.wmo.int/pages=TT-GISC-ops); and c) need to ensure that they meet the performance metrics for warnings etc in back up mode. | GISCs | CBS-16 |  |
| 16/1-6 | Action: a) GISCs should implement fast track changes within 6 months after the date of effect b) Secretariat should email notifications of approved fast track changes to TT-GISC email group | a) GISCs b) Secretariat | a&b) Ongoing |  |
| 16/1-7 | Action: GISCs to check their processes to ensure that any new metadata records only use a new/current date stamp | GISCs | Ongoing |  |
| 16/1-8 | Action: a) GISCs to provide a suitable style sheet to represent the returned SRU results as appearing to come from the centre using their SRU server; b) update SRU wiki pages to point to NZ SRU as an example of a centre using a GISC SRU | a) GISCs b) Secretariat | TT-GISC 2017 |  |
| 16/1-9 | Action: Ask a) TT-CAC to test GISC interfaces to ensure access controls conform to the WIS specifications. b) TT-CAC to work with GISCs to address any deficiencies | Secretariat & TT-CAC | TT-GISC 2017 |  |
| 16/1-10 | Action: Centres to notify the secretariat if they are interested in pilot for EduGain as academic user identification (GEOSS GD11) | GISCs | June 2016 |  |
| 16/1-11 | Action: Centres to notify the secretariat of planned training activities | GISCs | Ongoing |  |
| 16/1-12 | Action: a) GISCs to check if their implementation can cope with the two possible encodings of the WMO data policy (ie 1. to use gmx:Anchor and 2. free text:CharacterString). b) ask IPET-MDRD to consider this example and to avoid in the next version of WMO Core Profile multiple encoding styles for crucial information to minimize the implementation work for the GISCs. | a) GISCs b) Secretariat | a&b ASAP |  |
| 16/1-13 | Recommendation: GISCs should review the status of centres in their area of responsibility and assist the centres in notifying the secretariat. | GISCs | TT-GISC 2017 |  |