	WORLD WEATHER WATCH
COMMISSION FOR BASIC SYSTEMS
	[image: image1.png]World Meteorological Organization
Working ogethr i weathe,climts nd water






	
	

	Task Team on Aviation XML
Montreal, Canada, 7-9 October 2013
Submitted by: Enrico Fucile, ECMWF
	TT-AvXML-3/Doc11
Agenda Item 4

	
	26 September 2013


Document No. [XX] (Page 2)

Work plan to achieve approval of standard by WMO and ICAO
Plan
1. Version 1.0 of WMO AvXML has been released on WMO wis-wiki web site with tutorials and some documentation to allow tests to start.Agreed the format and content of new Vol. I.3 of WMO Manual on Codes .

2. WMO codes registry released.
3. Agreed the format and content of non-regulatory WMO document "Guidelines on WMO data modeling" to record the WMO Logical Data Model.
4. First draft Vol. I.3 of WMO Manual on Codes by January 2014.
5. First draft of "Guidelines on WMO data modeling" by December 2013
6. Final version of Vol. I.3 of WMO Manual on Codes by March 2014

7. Final version of "Guidelines on WMO data modeling" by February 2014

8. Documents to be submitted to WMO general meeting by April 2014: …
[image: image1.png]