## Slide 1
ET-CAC Report
2018-2019

## Slide 2: ET-CAC Meetings
ET-CAC meeting held in Wellington 1-4 Oct '18
  Review of generic audit process
  Tentative timetable for 2nd round of GISC audits drawn up
  Audit training for team members
  Next meeting scheduled for Oct 2019 in Seattle

## Slide 3: Activities
Audits
  DCPC audit activity has been very slow – 13 centres in Trello yet to start, 6 under way (but little/no recent activity).
Coordination
  Chair ET-CAC attended the ET-WISC and TT-DC meetings in Beijing in March 2019.
  Assisting in the development of audit criteria for next round of GISC audits

## Slide 4: Key plans for 2019-2020
Audit Planning:
  Assist with finalizing the GISC audit criteria and check lists.
  planning for 2nd round of GISC audits (Oct 2019)
  Commence 3-year audit programme to recertify all GISCs (5 per year).
Generic Audit Process
  Assist other CBS teams to define audit criteria for their audit programmes e.g. GDPFS Centres

## Slide 5
Thank you
Merci