# TT-GISC Action Items

## Action Required

Participants are requested to review the TT-GISC Action Items and to update status of each item.

| Action Number | Decision/recommendation/ action | Responsible | Objective/ deadline | Status As of August 2019 |
| --- | --- | --- | --- | --- |
| 14/1-12 | Action: c) TT-GISC members to participate in Cloud project Noting that national development of cloud based services by individual GISCs is of interest to all GISCs, TT-GISC should clarify the relationship between cache in cloud and WIS 2.0 then it could facilitate the coordination and knowledge gained from these national activities for consideration of international processes. Noted the risk of single supplies TT-GISC recognizes that we have to look at things now for the future and we have to take these in consideration. The funding mechanism for the cache in the cloud project was of a concern. Ideas of GISCs putting Ken to develop a paper describing what JMA want to achieve and provide to TT-GISC, possibly online discussion or telco next year and further refinement prior to TT-GISC Develop terms of reference for the project coordination and Its outcomes | c) Participating GISCs | Close this action and look at specific task on Ken for consideration for new WP in 2019 | CLOSED |
| 14/1-17 | Action: TT-GISC recommended: a) GISCs should agree on a single standard to facilitate user federation; b) Establish group to investigate, including establishing basic use cases c) Confirm elements needed to be shared. | Now under WP 3 | Report back to TT-GISC 2019 and to ET-WISC 2019 | Closed New opportunity under eduGain project. Action under WP 3, broadened to include federation, user information requirements and interaction with 3rd parties such as EduGain. |
| 14/1-21 | Recommendation: TT-GISC recommends that WMO be registered as a DCPC with a principal GISC of Toulouse. | Secretariat and ET-WISC. | Leave on agenda | CBS approved, Meteo-France agreed to be Principal GISC, WMO still working out internal processes through Library –no change in 2019 |
| TT-GISC 2016: Melbourne, Australia 18-22 April 2016 |  |  |  |  |
| 16/1-1 | Recommendation: TT-GISC noting that aside from the twice yearly monitoring survey and annual corporate survey, there are many other surveys making their way to GISC staff. It asked the secretariat to try and coordinate these additional surveys to minimise work on staff. | Secretariat | Ongoing | CPDB is schedule for completion end of 2019 and should see improvement |
| 16/1-4 | Action: All GISCs to: a) liaise with DWD to create their accounts and to make internal arrangements so that process works during backup mode. b) make accounts with Moscow and Tokyo who are running the same service. | GISCs | CBS-16 | Closed Work has been done. |
| 16/1-5 | Action: GISCs to advise TT-GISC of: a) their back up arrangements based on the spread sheet so GISCs can follow up; b) add this to the TT-GISC wiki GISC Ops page (http://wis.wmo.int/pages=TT-GISC-ops); and c) need to ensure that they meet the performance metrics for warnings etc in back up mode. | GISCs | CBS-16 | Close Data updated this meeting and will be put on ops page by secretariat asap |
| 16/1-8 | Action: a) GISCs to provide a suitable style sheet that can be run on the centres server to present the returned SRU xml results as appearing to come from the centre in a structure format, or to have the centres profile appear on the GISC based response, using their SRU server; b) update SRU wiki pages to point to NZ SRU as an example of a centre using a GISC SRU | a) GISCs b) Secretariat | TT-GISC 2017 | Closed Action item was unclear in terms of what GISCs are expected to do. |
| 16/1-9 | Action: Ask a) TT-CAC to test GISC interfaces to ensure access controls conform to the WIS specifications. b) TT-CAC to work with GISCs to address any deficiencies | Secretariat & TT-CAC | TT-GISC 2017 | Close Include as a part of the second round certification of GISCs |
| 16/1-11 | Action: Centres to notify the secretariat of planned training activities | GISCs | Ongoing | Close, post reports are in annual GISC report Encourage GISCs to advise in advance (WP 7) |
| 16/1-12 | Action: a) GISCs to check if their implementation can cope with the two possible encodings of the WMO data policy (ie 1. to use gmx:Anchor and 2. free text:CharacterString). b) ask IPET-MDRD to consider this example and to avoid in the next version of WMO Core Profile multiple encoding styles for crucial information to minimize the implementation work for the GISCs. | a) GISCs b) Secretariat | a&b ASAP | Noted that GISCs cannot easily manage duplicate ways of encoding policy Secretariat following up with metadata working groups but focusing on avoiding creating similar problems in future. Close item |
| 16/1-13 | Recommendation: GISCs should review the status of centres in their area of responsibility and assist the centres in notifying the secretariat. | GISCs | TT-GISC 2017 | Close as Being done. Note GISC should include the status of centres in their AoR |
| TT-GISC 2018: Casablanca, Morocco 18-20 September 2018 |  |  |  |  |
| 18/1-1 | The development of WIS 2.0 is to be led by TT-eWIS but all the GISCs need to ensure that they participate in the process. | GISCs |  | Continue |
| 18/1-3 | Japan (Tsunoda) will arrange for their project plan to be translated into English and make available to TT-GICS for discussion, to be led by the chair. | Chair | Report back to TT-GISC-2019 | Done: Meeting noted that JMA project is a very good WIS 2.0 pilot on cloud and pub/sub, but is not the same project as 14/1-12 Close |
| 18/1-9 | Mr Osuský will provide further information to TT-GISC on how to implement suitable sitemaps on their Members’ public web‎‎ and GISC Portals. | Mr Osuský under WP2 |  | Close TT-GISC2019. DWD implemented. See Decision |
| 18/1-10 | Subset of 18/1-9: GISCs are to implement these measures as soon as possible and report back to TT-GISC on implementation. | GISCs |  | Ongoing |
| 18/1-11 | The meeting agreed to review the WIS catalogue synchronization at the next TT-GISC (i.e. 2019) | GISCs, under WP5 | Report to TT-GISC | 2019 Done - Ongoing |
| 18/1-12 | TT-GISC encouraged all GISCs to share their training material with the WP 7 team for the creation of a shared repository for review by TT-GISC2019. | GISCs, under WP7 | TT-GISC2019 Link to ET-WISC 19/1-4 | 2019 ongoing |
| 18/1-13 | The meeting noted the concern of Tokyo relating to HTTPS access between GISCs asked each GISC to confirm the status of access to other centre. | GISCs |  | Still a problem, but metadata synch addressed by new two authoritative gisc catalogues one each serving http and https |
| 18/1-14 | The changes in Annex 8 should be made to the GISC Operations Page and to the GISC Ticket System. | WP6, Sec |  | Done |
| 18/1-15 | Secretariat to add the updated GISC Backup Matrix to the GISC Operations Page. | Sec. | By each TT-GISC meeting | Ongoing |
| 18/1-17 | The meeting established a new Work Package, WP-8 (Technical Regulation updating) to draft recommendations e.g. WIS monitoring (Tech-spec-15), Jason-Spec and so on. | WP8 | Link to ET-WISC 19/1-5 | On going |
| TT-GISC 2019: Offenbach, Germany 26-29 August 2019 |  |  |  |  |
| 19/1- |  |  |  |  |
| 19/1- |  |  |  |  |
| 19/1- |  |  |  |  |
|  | A1 Requested Chair ET-WISC to report to ICT-ISS on the position of GISCs relating to constituent body reform structure and proposed TOR. A2 The meeting agreed to holding a break out session to review User Federation, including investigating the work on use of EduGain and reviewing what user information should be mandatory and what should be optional. A3 Secretariat (Enrico Facile) to follow up with the metadata working group, advising them to avoid similar traps in future editions. A4 TT-GISC to advise Tehran on steps that should be taken to request and establish a back up GISC. A5 TT-GISC requested GISCs GISCs Brasilia, Jeddah, Melbourne or Pretoria to upload their reports as soon as possible in order to meet the reporting requirements laid out in the WIS Manual and Guide. A6 Kai to update GISC Ops Page to include the new items. A7 The meeting requested that listed GISCs migrate remaining metadata in WIS-UNASSOCIATED to principal GISCs, and GISC A8 The secretariat should advise the metadata working group on search of the success and lessons learnt from use of site maps. A9 Mr Francis to circulate a report of the break out group meeting to the group before November 2019. A10 TT-GISC will review the WIS catalogue synchronization on the next TT-GISC (i.e. 2020) to check if any improvement and if so will propose update of the WIS manual to clarify the role of “WIS catalogue authority”. A11 The meeting encouraged all GISCs to keep providing information to the training aids pages. A12 TT-GISC requested the chair of ET-WISC to brief ICT-ISS on the above decisions and to seek permission to deprecate WMD profile 1.2, and have TT-GISC migrate existing 1.2 metadata to version 1.3 |  |  |  |

## References

[1] Xxx URL (Date accessed)

[2] Etc

## Recommended Text

[Include here suggested text for inclusion in Report, including any proposed amendments to the Manual or Guide to WIS, Manual on GTS or guides.]

--------------------