## GISC+ISSUE+TICKETS
as of 1st July 2019
ID | Project | Assigned To | Summary | Status | Resolution | Response from assigned GISC and status | issue | comment/suggestion
7 | GISC ISSUE TICKETS | gisc_seoul | 2018-6: No response (OAI-PMH), PORTAL and SRU for >= 4 days Seoul - Melbourne | new | open | Seoul and Melbourne understand the issue, but they need some time to analyse solutions. (Seoul and Melbourne might not synchronize metadata each other) | Metadata sync. Network, protocol | Seoul to change its status from "new" to acknowledged or confirmed.
8 | GISC ISSUE TICKETS | gisc_melbourne | 2018-7: No response (OAI-PMH) ,PORTAL and SRU for >= 4 days Melbourne - Seoul | new | open | Melbourne and Seoul understand the issue, but they need some time to analyse solutions. (Melbourne and Seoul might not synchronize metadata each other) | Metadata sync. Network, protocol | Melbourne to change its status from "new" to acknowledged or confirmed.
14 | GISC ISSUE TICKETS | gisc_tokyo | 2018-12: No response (OAI-PMH) for >= 4 days Tokyo - Tehran | acknowledged | open | Tokyo does not accept port:8080. (Tokyo can not harvest Tehran's metadata) | Metadata sync. Network, protocol | Tokyo to discuss with Tehran directory on this (and No.14) to share common understanding.
20 | GISC ISSUE TICKETS | gisc_tokyo | "Size of Data & Products in 24h Cache" is showing zero size for past month | acknowledged | open | Tokyo understands the issue, but they need some time to resolve it. | Json creator, software | Tokyo to provide estimation date, if possible.
23 | GISC ISSUE TICKETS | gisc_tehran | No response (OAI-PMH) with several GISCs from GISC-Tehran | assigned | open | GISC Tehran provided their URL of OAI provider and is following up this issue with these GISCs. (Tokyo and Exeter might not harvest Tehran's metadata) - For Exeter, not sure the cause of issue. - For Tokyo, it's same as No.14. | Metadata sync. Network, protocol | Tehran to change status from assigned to confirmed. Exeter to check Tehran's URL on your system. Tehran and Tokyo to have discussion (see No.14)
29 | GISC ISSUE TICKETS | gisc_exeter | No response (Portal) for >= 4 days Exeter - Tokyo | acknowledged | open | Exeter still need to fix their system to connect via https to GISC Tokyo and needs a long time to adopt https access. | Network, protocol | Exeter to change status to confirmed.
31 | GISC ISSUE TICKETS | gisc_beijing | "no response" to the OAI-PMH from Casablanca, Melbourne and Exeter to Beijing for at least 4 days | assigned | open | Beijing provided their new URL of OAI-PMH provider (http://gisc.wis.cma.cn/wis/provider) (metadata from Casablanca, Melbourne and Exeter might not be harvested by Beijing) | Metadata sync. Network, protocol | Beijing to change status from assigned to acknowledged. Relevant GISCs may need to connect to Beijing's new URL. It's better to issue individual ticket for each GISC.
33 | GISC ISSUE TICKETS | gisc_pretoria | Error in OAI ListIdentifiers Response | assigned | open | The problem seems to be solved. Pretoria is requested to confirm. | GISC watch | Pretoria to confirm the latest status, and then to change status to "resolved". on Duty GISC to confirm status and to consider closing No.33
38 | GISC ISSUE TICKETS | gisc_pretoria | No response from GISC Pretoria | assigned | open | No response from GISC Pretoria. GISC Beijing, Casablanca, Exeter, Melbourne, Moscow and Toulouse may not know the Pretoria's SRU URL. | Json file | Pretoria to review the ticket and to change status from assigned to acknowledged. Pretoria to create and provide json files.
43 | GISC ISSUE TICKETS | gisc_exeter | No response (sru) from Tokyo to Casablanca, Melbourne and (portal, oaipmh,sru) to Exeter for >=4 days | assigned | open | Exeter, Casablanca and Melbourne is to adopt https. Three centres may not harvest metadata from Tokyo. - For Exeter, it's same as No.29 - For Casablanca, they confirmed the issue. - For Melbouree, no response from Melbourne. | Metadata sync. Network, protocol | It's better to sprit this ticket into two. 1) for Casablanca. 2) for Melbourne. Exeter (see No.29)
45 | GISC ISSUE TICKETS | gisc_delhi | New Delhi missing files | assigned | open | No response from GISC New Delhi (New Delhi might not harvest metadata from all other GISCs.) | Metadata Sync | New Delhi to review the ticket and to change status from assigned to acknowledged.
47 | GISC ISSUE TICKETS | jmauro.rezende | No response from Washington to Brasilia for >=4 days | resolved | fixed | The duty GISC can not assign a ticket to GISC Washington. Washington doesn't have a Mantis account yet. JMauro will request Tokyo and Beijing to add Wasington into their WCD table. (probably, also Jeddah, New Delhi and Pretoria) | Mantis ID | on Duty GISC can close this ticket (No.47), but need to issue new tickets. 1) request Washington to provide Brasilia with account information to use the ticketing system. 2) request Jeddah, New Delhi, Pretoria and Washington to create and provide json files.
53 | GISC ISSUE TICKETS | GISC-Jeddah | No response (OAI-PMH,Portal, SRU) for >= 4 days Jeddah to all centres | assigned | open | No response from Jeddah. Jeddah has not been providing OAI, Portal and SRU services for at least six months. | not providing web service | Jeddah to review the ticket and to change status from assigned to acknowledged and provide current status to all GISCs. | high-priority
104 | GISC ISSUE TICKETS | jmauro.rezende | No response (OAI-PMH) with several GISCs from GISC-Brasilia >= 4 days | resolved | fixed | seems to be solved. | GISC watch | on Duty GISC to confirm status and to consider closing No.104
109 | GISC ISSUE TICKETS | gisc_exeter | Harvesting not possible | assigned | open | No response from Exeter. | GISC watch | Exeter to review the ticket and to change status from assigned to acknowledged.
110 | GISC ISSUE TICKETS | gisc_toulouse | JMA-WCD - GISC Response Monitor | assigned | open | Offenbach changed protocol from http to https. Casablanca, Exeter, Melbourne, Moscow, Seoul and Toulouse could not adopt https. There is no information from above GISCs. | Network, protocol | this ticket should be issued individually, for Casablanca, Melbourne, Moscow, Seoul and Toulouse. For Exeter (see No.29 and 43)
111 | GISC ISSUE TICKETS | gisc_seoul | OAIMonitor - Harvesting Problems | resolved | fixed | seems to be solved. |  | on Duty GISC to confirm status and to consider closing No.111
114 | GISC ISSUE TICKETS | gisc_beijing | Issues in WCD system | assigned | open | No response from Beijing. | WCD at Beijing | Beijing to review the ticket and to change status from assigned to acknowledged.
115 | GISC ISSUE TICKETS | gisc_brasilia | GISC Brasilia will back metadata up from GISC Washington | assigned | open | There is no follow up action. |  | Brasilia to review the ticket and to change status from assigned to acknowledged.
117 | GISC ISSUE TICKETS | gisc_beijing | No response (OAI-PMH,Portal, SRU) for >= 2 days beijing to all centres | assigned | open | Beijing resumed the service. | not providing web services | Beijing to change status to resolved. on Duty GISC to confirm status and to consider closing No.117 | high-priority
118 | GISC ISSUE TICKETS | gisc_moscow | No response (OAI-PMH and SRU) for >= 4 days Moscow to Exeter | assigned | open | No response from Moscow nor Exeter. (Exeter may not harvest metadata from Moscow) | Metadata sync. Network, protocol | Moscow or Exeter to review the ticket and to change status from assigned to acknowledged.
119 | GISC ISSUE TICKETS | gisc_offenbach | No response (OAI-PMH,Portal, SRU) for >= 4 days Offenbach to Casablanca,Exeter,Melbourne,Moscow,Seoul and Toulouse | resolved | open | same as No.110 | Network, protocol | same as No.110. on Duty GISC to close this ticket No. 119.
120 | GISC ISSUE TICKETS |  | No response (OAI-PMH,Portal, SRU) for >= 4 days Washington to all centres | new | open | Duty GISC can not assign a ticket to Washington. see No.47 | not providing web services | Washington to provide all GISCs with current status at Washington. Washington to get a Mantis ID and change status from new to acknowledged. See No.47 | high-priority