## Slide 1
TT-IM introduction

## Slide 2: Task Team on Information Management - ToRs
Collaborate with technical commissions to review available information management practices and develop and document appropriate standards and practices in information management;
Recommend procedures for the long term maintenance and development of standards and best practices related to information management;
Replace the “Guide on World Weather Watch Data Management (WMO No. 788)” with a new guide on best practices for information management across all WMO programmes;
Propose updates to incorporate standards and practices for information management under WIS Part C in the Manual on WIS (WMO No. 1060) and Guide to the WIS (WMO No. 1061);
Recommend updates to the WIS competencies related to information management and associated training and learning guides.

## Slide 3
Identify how
  WMO can monitor trends for ICT technology and data and provide briefing notes on the emerging challenges and issues.
  Be aware of the challenges and opportunities from emerging ICTs in supporting efficient IM.
Identify how WMO can maintain awareness of emerging challenges and issues relating to ICT technology and data and produce technology review notes on these.

## Slide 4: Provisional timelines and workplan
2,3,4 Oct. IM workshop
5-6 Oct. TT-IM meeting
  Draft structures of part C of Manual on WIS
  List of additional Guides ?
Week of 15 January 2018: ICT-ISS meeting
  review draft structure of Manual & Guides on IM and prepare CBS TECO
Week of 26 March : CBS TECO
  Present high level structure of Manual and Guides on IM and get input from CBS
April : integrate comments from CBS and CBS MG

## Slide 5: Provisional timelines and workplan
End of June : EC
  Present high level structure of Manual and Guides on IM and get input from EC
July 2018 - March 2019 : TT-IM activities
  integrate comments from EC
  2nd meeting of TT-IM (joined meeting with TT-WDP and IPET CDMP ?)
    consolidated version of Manual and Guides with key items of each chapter of the guide
  Circulate guide to TT-WDP and IPET-CDMP and CBS MG and get comments
  Prepare final high level version of Manual and Guides and circulate for comments within members before submission to Congress

## Slide 6: TT-WDP Phase 2 ToRs
Consider current and emerging information and communications technologies (ICT), best practices for strategic data management and emerging trends in data and its use,
Develop WIGOS guidance material on Data Management and Data Stewardship on:
  the role of WIS, NMHS and partner systems in the data lifecycle
  best practices for data integrity and data preservation
  the challenge and opportunities of ‘Big Data’ and associated emerging trends in relation to data and its use
  models and best practices in data stewardship (roles, responsibilities for data governance)
  matters of compatibility among the legacy and emerging data management practices of the various WMO Programmes and Commissions (e.g. CBS, CIMO, CCl, CHy)
On emerging data issues (e.g; Big data, crowdsourcing, commercial data, …) maintain awareness of the activities and align guidance material with the direction of the Executive Council Task Team on Data Policy and Emerging Issues (EC TT-DPEI), the perspectives of Technical Commissions, and subsequent actions by CBS

## Slide 7: TT-WDP input
High level diagram that shows how the different element fits together
Interoperability with other forms of data
Cultural shift around security and data sterwarship ..separate function and technics
Data licensing
Data policies
Different quality in data
  Make sure that the system can deal with different quality data
Open data management. Is it different?

## Slide 8: TT-WDP input
Change management process
  procedural and human communication and obviously the technical aspect of data management
Traceability of the management system
  Everything is traceable in the management system
Provenance
Accommodating the diversity of the members
Do not forget metadata ….
Initial guide identifying the most critical area allowing members to understand the key aspects of data management.
Single authoritative source …. Whatever the processing

## Slide 9
Thank you
Merci