| World Meteorological Organization COMMISSION FOR BASIC SYSTEMS Expert Team WISC 13-17 November 2017, Geneva | ET-WISC2017/Doc -8(1) |
| --- | --- |
|  | Submitted by: Secretariat 01.11.2017 |

# Report from Task team on Information Management

(Provided on behalf of William Wright, Co-Chair CBS Task Team on Information Management)

The first meeting of the Task Team – Information Management took place on 5-6 October, and followed the WMO Workshop on Information Management. The main outcome was a plan to develop material for a Manual on Information Management. In order to have at least some deliverables ready for the CBS Technical Conference in March 2018, it was agreed that the scope of the Team's endeavours over the next three months should be to frame a structure and outline for the Manual and associated guidance materials, arranged along the lines of a Maturity Matrix.

Nine key Topics (subsequently condensed to eight), corresponding to required competencies in the Maturity Matrix, were identified, and for each topic it was agreed that team members would:

  - Describe why they were important;

  - Describe what the topic should cover;

  - Identify and describe a number of Aspects to each topic, and why they are important;

  - For each aspect, identify typical behaviours that correspond with each of five competency levels (from basically unorganized through to best practice).

The Topics, along with columns for Aspects and Behaviours, are shown in Annex 1: TT-IM work plan (to CBS-TECO).

A lead author was assigned to each of the topics (as identified in the final table of Annex 1). Their initial task is to identify and describe the aspects corresponding to their topic. Members of TT-IM will review early drafts and provide suggestions to the Leads. This task will need to be completed not later than about mid-November –(17 November 2017). TT-IM plan also to identify characteristic behaviours for each aspect in subsequent drafts.

Lead Authors are requested to:

  - Review the descriptions under "Categories" for your topic (Column 1 in the Annex 1), and edit as needed;

  - Supply the key elements that go with each topic, under "Aspects" (Column 2). These were generated during the Breakout sessions at TT-IM-1. Further details can be found in the informal meeting notes ("Steve notes" in the Meeting Documents section on the TT-IM-1 meeting page)

  - Provide a few bullet-points for each Aspect (2nd column), describing why it's important and what it means (i.e., what guidance would be covered by it). For instance, for "vocabularies" under Documentation, we might describe it as something like:

- Vocabularies are important to ensure a common understanding between users of what different terms and processes mean (e.g., quality control).

- Develop an agreed list of terms and agreed definitions.

- Adopt existing terminology where it exists and is widely understood, but develop new definitions where necessary

  - Lead authors will then convene via teleconference during mid-November to agree the Aspects.

Following this, the procedure will be:

  - Identify maturity "Behaviours", which comprise the "performance standards" for each level of competency in the maturity matrix. For instance, for "Access and Sharing" we speculated in our meeting that the behaviours might be "Case by case, ad hockery "(lowest level); "Bulk download" (2nd level); "Web services on someone else's site" (3rd level); "Access toolkit on someone else's site" (4th level); "Hosting catalogue on own site" (highest level of maturity).

  - Allocate writing tasks to Team Members address those topics identified as requiring additional urgent guidance material.

  - Provide one row of the Maturity Matrix ready as an example for the ICT-ISS meeting scheduled for mid-January, where work of TT-IM will be reviewed. Therefore all writing tasks would essentially need to be completed by end 3rd week December.

____________

# Annex 1: TT-IM work plan (to CBS-TECO)

- Aim for TECO: all Categories and Aspects defined. Strawman behaviours – but one row of maturity matrix filled in as an example. First draft for ICT-ISS meeting

| Categories | Aspects | Behaviours |
| --- | --- | --- |
| Documentation Documentation is important so that: - users can find, understand and use the data and associated services (metadata) - data are processed / produced in a consistent way (including guidance for new staff) (QMS) - users can trust the data they use (and you can defend yourself in court) (provenance) You need to include in your documentation of data: - How it was produced and processed, how it is managed, ownership, how it is accessed, who can use it and what how they may use it, what application areas it is intended to support, services available, its quality and how that is assured, what it contains, what data were used to create it, where to go for help | Document your procedures (and retain documentation) - Important, because provides a traceable ongoing record of how and why things were done - And provides a source for “on the job” reference and training - Ensure each new information management-related project includes a documentation component - Establish a documentation archive - retain code and algorithms vocabularies - Vocabularies are important to ensure a common understanding between users of what different terms and processes mean (e.g., quality control). - Develop an agreed list of terms and definitions. - Adopt existing terminology where it exists and is widely understood, but develop new definitions where necessary standard ways of describing datasets inventories intended use maturity |  |
| Governance We need governance so that: - Your investment in gathering, processing, storing and exchanging data delivers value - Irreplaceable information is available for future generations - Risks associated with information production and use are managed (… IPR, traceability,…) - Saves effort and increases operational efficiency through clear understanding by staff of what is expected and permissible - Your information assets are managed so they achieve what you want and to reduce your risks associated with them - P18 CDMS spec. People can use the data over a long period (sustainability) To achieve this Governance has to cover: - Consistent approaches to processes – facilitate authoritative data – sharing and integration - clear IPR issues – data access – data usage – process for integrity – long term sustainability - Accountabilities and responsibilities - Data policy - Clarity on standards to be used (national and international) - Funding model - National/international commitments |  |  |
| Information storage ICT operations deliver: |  |  |
| Storage and Preservation We need managed storage and preservation so that: - Data content and associated contextual information are trustworthy, available and usable when needed, now and in the future - Policies on use and retention can be applied Managed storage and preservation has to cover: - P40 cdms: backup, restore, redundant copies, retention, technology migration, capacity management, long term accessibility, (competent – individual, corporate), storage strategy, controlled ingestion process, access controls, archive, deletion of data no longer to be retained, accountabilities and responsibilities, technology exit strategies (eg cloud) |  |  |
| Quality management We need quality management so that: - Data and related contextual information are, and can be demonstrated to be, fit for purpose (complete, accurate, …) Quality management has to cover: - Documented decisions, audit, quality related procedures, algorithms, definition of quality measures, required contextual information (quality managed using same principles as data) (including metadata, “engineering” data…..), monitoring data (being received, stored appropriately, …), feedback mechanisms to providers, metrics (summaries of quality control findings), assessing uncertainty, verification, (may need notes in the text to explain equivalent terms in different disciplines), standards to be applied (and conformance audited, eg ICAO), “usability”, provenance of data and software used in creating products - Peer review of data, algorithms and processes where appropriate | how decisions are made, what decisions are made, how decisions are recorded |  |
| Access and sharing We need access and sharing so that: - Data can be used by the appropriate people and software systems where and when it is needed - Data can support delivery of societal benefits Access and sharing has to cover: - Exchange “conventions” (open formats, data models, machine-to-machine interactions, web services, etc ), community agreed ways of working together using open standards, - Protection of data in transit, access control (supporting usage conditions), promote open data, - Methods of access suitable for intended user communities (consider the access from the perspective of users) - Tracking delivery and use - Compliance with policies and regulations - [telecoms should already be covered by the WIS centre regulations] - Cost recovery models - Controlled vocabularies | DoIs |  |
| Discovery We need discovery so that: - Data providers can deliver additional societal value through reuse by others of their data, and their contribution can be recognized - Data providers can publicize the data and associated services that they are offering - Users can find efficiently the data most suitable for their needs - Duplication of effort in creating data can be avoided Discovery has to cover: - Inventory, contextual information, user focus, controlled vocabularies, catalogues searchable by commercial search engines, access to documentation and data, meeting community conventions, web page, operating a catalogue, catalogue-catalogue interaction, usage statistics and feedback on search experience , currency of information in catalogue | put list on web page use other’s catalogue use own catalogue host others’ info in your catalogue |  |
| Change management We need change management so that: - Users can have confidence in the data - Users know when and why changes are made to data they use - We understand what changes have been made and we have traceability of those changes Change management has to cover: - ICT change management must not corrupt or change the meaning of data (underpinning factor), intensity of change management/provenance depends on the data being managed, authority to change and controls over change, recording of changes, notifications of changes, - Don’t delete the original data – flag it. |  |  |
| Competences We need to ensure that people and suppliers supporting our data: - Have the knowledge to do the tasks required of them - Have the ability to apply the knowledge to deliver the tasks required of them - Add to the competences already in the WIS manual Competences need to include: - Quality management - Storage/database management - Data change management - Documentation/ context information management - Data governance |  |  |

- Need section of WIS Manual on ICT operations (includes restructure to pull things “up” from the audit criteria – ET-WISC coordinate?). Do we need to draw together a theme in WIS monitoring documentation? Change management in IT operations

| Categories | Responsibility |
| --- | --- |
| Documentation | Will |
| Governance | Will |
| ICT operations |  |
| Storage and Preservation | Julie |
| Quality management | Gao |
| Access and sharing | Jeremy |
| Discovery | Kate |
| Change management | Dimitry |
| Competences | Thorsten |