## Slide 1
Progress Report on the Task Team on Information Management
William Wright, Australia
w.wright@bom.gov.au

## Slide 2: Contents
What the TT-IM (Information Management) seeks to accomplish
General approach
Work to date
Going forward (next steps)
Issues
Recommendations

## Slide 3: What the TT-IM seeks to accomplish
Primary aim is to replace the Guide on WWW Data Management with a new Manual on best practices for IM
Considers IM across all WMO Programmes
Recommend improved standards and practices for IM under WIS Part C
Define competency standards on IM

## Slide 4: What we'd like from ICT-ISS
Endorsement that the TT-IM and its workplan are heading in the right direction, by endorsing the proposed approach, work to date and mooted next steps; and/or
To provide suggestions and comments or alternatives on the proposed way forward.

## Slide 5: General Approach
Manual and competencies to be based around maturity matrix for eight high level topics, each a requirement for high quality data/information sets
The 8 requirements were identified in a preceding CCl/CBS joint workshop on IM. By identifying aspects of each requirement, the framework for the Manual contents is defined.
Aim is to describe what each aspect means in practice, and identify required behaviours and competencies for each, ranging from basic through to advanced.
WIS centres are to be assessed against the topics and aspects of the maturity matrix, which will form the substance of future regulations

## Slide 6: Eight identified practices in high quality data and information management
Good documentation, describing consistent well-defined practices
Good governance - standards, policies, accountabilities, authorisation, compliance mechanisms
Effective storage and preservation
Effective quality assurance processes
Accessibility and sharing mechanisms
Discoverability
Accountable change management processes and provenance
Adequate competencies and training

## Slide 7: Work to date
The two-day TT-IM meeting in early October workshopped the various Aspects of each of the eight core requirements
Lead authors were then appointed to describe in more detail what each Aspect means
Next step is for TT as a whole to agree the Aspects

## Slide 8: Proposed next steps
The Behaviours corresponding to 4-5 competency levels for each Aspect will be identified and described
This detailed content will comprise the explicit guidance. Where they exist and are appropriate, links will be made with existing manuals, standards, etc.
Team will endeavour to draft one complete row of the maturity matrix (i.e., a complete set of Aspects and Behaviours for one topic) by EC, by way of a proof of concept for the proposed approach

## Slide 9: Proposed next steps (Cont'd)
Regulations, describing the high-level requirements, will be drafted post-EC and put through a formal consultation process late in 2018.
Goal is to have these ready for approval by Cg-18.
Remainder of guidance will likely be exposed on the Web during 2018 and early 2019, and feedback and road-testing encouraged
Aim is to have this endorsed through in-session procedures at the CBS session following Cg-18.

## Slide 10: Issues
Usual issue of having team members complete assignments and deliverables within time-frames
Ongoing coordination with other Technical Commissions, especially the CCl's High Quality Global Data Management Framework for Climate
Process for updating Guidance, to ensure required competencies stay aligned with emerging new ICT capabilities
Training requirements and arrangements

## Slide 11: Recommendations
That the ICT-ISS endorse the proposed approach and proposed next steps of the Task Team, and/or provide suggestions on alternative approaches.
That consideration be given to ensure alignment and synergy with other WMO activities in the Information Management space, e.g., CBSLT-EDI, IPET-CDMP

## Slide 12
Thank you
Merci