## Slide 1: ET-CTS - Cache in and through the cloud Contractual aspects
ICT-ISS – Geneva 16-18 Jan 2018

## Slide 2: Iterative approach
Operation of the cloud service should be step-by-step transition (as prescribed by the WIS 2.0 implementation strategy)
Initial stage:
  All GISCs participate.
  Add data meant for Global Exchange.
  Add Metadata to the cloud.
Evolution stages:
  Incorporate some of the concepts of WIS 2.0.
Final stages:
  Subscription to data/products by users.
  Meet WIS 2.0 requirements.
Initial stage
Evolution stage
Final stage
2019 - 2022
2025-?
2022 – 2025 ?
Notes: Scope of data included in each phase of the project and access are controlled by metadata keywords set by originating centre/data provider:
  WMO_DataLicenseCode – whether or not the data is considered essential and if the data has associated licensing/access constraints
  WMO_DistributionScopeCode – level of data exchange (global, regional, centre)
  WMO_ProductCategoryCode – GTS priority level (also determines if QoS mechanisms are required)

## Slide 3: Financial strategy
For expedience during « initial phase », WMO to run a tender on behalf of the 15 GISCs
A « trust fund » mechanism to be implemented to handle the money stream
Define a cost splitting arrangement between GISCs (action to TT-GISC)
GISCs will require a level of certainty in terms of cost implication with this solution
Outstanding actions: Execute the tender, determine successful vendors, and determine baseline costs
Check with GISCs regarding “value for money” of the solution before contracting with the proposed vendor

## Slide 4: Why a “trust fund” ?
Even if the service will be for operation within WIS 1.0 framework, it must be seen as a pilot of cloud technologies for WIS 2.0
Considering the financial aspects and the contractual challenges faced by some GISCs, a centrally managed contract by WMO is the only viable option
According to WMO procurement rules, before launching a tender, money must be available
The « trust fund » along with the commitment from the GISCs to pay is, therefore, the most practical way to proceed

## Slide 5: Planned approach toward the « Initial Phase » - 1
ICT-ISS - January 2018
  Present the project and the plan
WMO issues an RFI to obtain “not to exceed” values – responses by Feb. 15th
  Evaluate budget for the overall 3-year contract
    Include management cost, cloud infrastructure running cost, WMO management cost (contract, tender,…)
TECO – March 2018
  Get approval on the project and the plan
Paper for EC including – April 2018:
  Expected WMO support/role
  Agreed cost sharing solution
  Description of the project and expected benefits
EC - June 2018
  Endorse the concept and allow CBS to proceed once the financial commitment from the GISCs has been received

## Slide 6: Planned approach toward the « Initial Phase » - 2
Before launching the tender, obtain approval from GISCs with commitment to fund the contract for its entire duration (3 years) – October 2018
WMO issue a “Expression Of Interest” allowing pre-selection of potential bidders – October 2018
  Once potential bidders are identified, address conflict of interests among experts (if an NMHSs is selected no expert from that country should be involved in the tender)
Complete tendering documents – November 2018
WMO to issue the documents to the selected bidders – January 2019
Answers received – March 2019
Analysis of the answers and prepare tender report - May 2019
WMO to choose the successful tender – June 2019
Approval by CBS Management Group - Summer 2019
Commissioning - Initial phase – Late 2019 – mid-2020
Operational phase – Mid-2020 - 2022
By 2022, we should know what WIS 2.0 will look like and will be prepared the evolution phase. Requirements and funding arrangements will be re-discussed.

## Slide 7: Questions?