## Slide 1: Help us to help you!
Rémy Giraud
Network and Security Section

## Slide 2: We need Pilot Sites
A (maybe) new network with (maybe) a new provider will be a risky period for the RMDCN
In order to mitigate these risks, we have defined a pilot phase
We need sites to join the pilot network
  ECMWF
  2 or 3 Member States
  2 or 3 countries outside Europe
We need you!

## Slide 3: A challenging migration
In order to limit the long running phase with two networks, we have defined an “Accelerated Incremental Migration”
To do the migration in 4 months will require everyone on board
H1-2013: Defining the configuration and signing (if needed) the accession agreement
October 2013 – January 2014: the migration
We will define a short “no change” period around Christmas and New Year day 2014.

## Slide 4: Timeline

## Slide 5: 2013 planning
Project Kick-Off
January
Pilot sites agreed
January
Orders for pilot sites
15 March
Operational Service Commencement Date
mid-October
Tests for pilot, including pilot reliability acceptance tests
mid-May – mid-October
Acc. Agreement
for pilot sites (if needed)
January - March
Payment will start for all pilot sites
Deadline to submit orders to be part
of the Initial Deployment
1 July
Global network Acceptance Test
December - mid-January 2014
Individual handover of sites
before mid-December
For each site payment will start after site reliability acceptance tests

## Slide 6: DMVPN: a mitigating solution
As explained by Ahmed, DMVPN has already been in 3 occasions a very useful safety net for 2 sites
With the upcoming change, we strongly suggest that as many sites as possible to consider joining the DMVPN network:
  The financial implication are rather low (a Cisco router whose cost is less than 1000€)
  The local site will have to prepare a simple vanilla configuration
  Most of the configuration will be done by ECMWF
  Consider the technical requirements
    Can you provide a direct connexion (non NATed to the Internet)?
    Can you use an official IP address for the DMVPN router?
    With your security policy can you accept having the same hosts being reachable via a private network (RMDCN) and a public network (Internet)?

## Slide 7: Prepare your test PC
The architecture of your connexion to the RMDCN will typically looks like:
RASA (the test PC) must be on the same LAN where the CPEs are connected
You need to give an IP address in the same subnet used on the CPEs

## Slide 8: The project organisation
The migration project will be managed by ECMWF with the new provider
Each site will have an important role to play from the definition of the configuration to the migration
We maintain two email lists:, including the acceptance tests
In the technical requirement document we have defined a project organisation. For each site we will need:
  Local Project Sponsor
  Technical Architect
The “Local Project Sponsor” will have an administrative/management role
The “Technical Architect” will have a technical role
It could be the UserRep and the TechRep but can be other contacts if considered more appropriate in your organisation (e.g. project vs operation)

## Slide 9: Keep us informed with your organisation changes
In order to manage the network, we must know who are our contacts. We need three contacts:
  The 24/7 contact email and phone number in case of an incident
  The Technical representative (techrep) is in charge of all technical aspects of the configuration (IP addresses, the test PC, Class of Service…)
  The User Representative (userrep) deals with commercial and management aspects. The userrep can be used as an escalation point
Having a 24/7 contact is critical to make sure that incidents are managed efficiently
We maintain two email lists:
  userrep@lists.ecmwf.int
  techrep@lists.ecmwf.int
These mailing lists are used to inform all connected sites about the network. It is therefore important that the “right” persons receive the emails.

## Slide 10: Answer (quickly!!) to your emails
Before (H1-2013) and during the migration (H2-2013 and early 2014), we will need to contact you frequently about the upcoming changes, the configuration requirements, the accession agreement (if needed), the technical details of the solution,…
These contact will be done via email with the userrep and the techrep that have been designated.
We will need you for the migration to be successful.