| ET-WISC/01 | Determine the operational criteria for GISCs and DCPCs, and develop the procedures for periodic assessments to assess quality of services offered by WIS Centres, especially GISCs. Submit the first draft to CBS 2014 | TT-CAC |
| --- | --- | --- |

| TT-CAC Action Plan Reference |  | Action |  | Person (if identified) | status |
| --- | --- | --- | --- | --- | --- |
| TT- CAC/01 To be done nex | Complete audits and reviews of existing DCPCs and GISCs |  | Immediately after meeting Chair to contact Li Xiang Dave to provide progress report to telco. (June) |  |  |
| TT- CAC/02 | Update the document WIS DEMONSTRATION PROCESS PROCEDURES AND GUIDELINES (http://www-db.wmo.int/WIS/centres/guidance.doc) based on past experience |  | Target July Audit letter, template report, kevin’s process Review process diagram - Baudouin General review of text. – Kevin & Matteo Review the following in light of the process: Remy - Background – - Demonstration procedures – - Questionnaire guidelines - Demo test cases – Markus & Leon (Annex A) Telecon – Mid June to review the work Review Remy and Keven’s work. Aim to complete task by end of July for inclusion in CBS |  |  |
| TT- CAC/03 | Draft document on the procedure on rolling review of WIS centres |  | Done, to be finalized by Kevin. For inclusion. Provide comments in 2 weeks Kevin to review feedback Telco mid June to discuss. Add to guide |  |  |
| Guidance for TT members | See report to ET-WISC 2013 (http://wis.wmo.int/doc=2587 ) |  | Based on TT/CAC / 03, to be ready for next audit round |  |  |
| TT/CAC/04 | Update WIS centres and demonstration databases , included sample answers (remove) |  | Seek secondment (see doc/report) |  |  |
| TT-CAC/05 | Update check lists and tests |  | Based on CBS output. |  |  |