Comments on TT-CAC Work Plan

| TT-CAC Action Plan Reference | Action | Person (if identified) and status |
| --- | --- | --- |
| TT- CAC/01 | Complete audits and reviews of existing DCPCs and GISCs | Immediately after meeting Chair to contact Li Xiang Dave to provide progress report to telco. (June) Status, all updates were made for CBS and MoW updated. Cg17 approved the changes but gave centres not audited another year. |
| TT- CAC/02 | Update the document WIS DEMONSTRATION PROCESS PROCEDURES AND GUIDELINES (http://www-db.wmo.int/WIS/centres/guidance.doc) based on past experience Version 0.5.4 published 29 Apr 2015 replacing ET-GDDP with TT-CAC. Not sure about other issues. | Target July Audit letter, template report, Kevin’s process Review process diagram - Baudouin General review of text. – Kevin & Matteo Review the following in light of the process: Remy - Background – - Demonstration procedures – - Questionnaire guidelines - Demo test cases – Markus & Leon (Annex A) Telecon – Mid June to review the work Review Remy and Kevin’s work. Aim to complete task by end of July for inclusion in CBS |
| TT- CAC/03 | Draft document on the procedure on rolling review of WIS centres | Done, to be finalized by Kevin. For inclusion. Provide comments in 2 weeks Kevin to review feedback Telco mid June to discuss. Add to guide Done - Cg-17 approved. Updated MOW and Guide with editors |
| Guidance for TT members | See report to ET-WISC 2013 (http://wis.wmo.int/doc=2587 ) | Based on TT/CAC / 03, to be ready for next audit round not sure of status |
| TT/CAC/04 | Update WIS centres and demonstration databases , included sample answers (remove) | Seek secondment (see doc/report) France offered but have not had internal resources (ie time) to analyze and prepare statement of work, mainly because lack of knowledge on what WMO overall db solution is. |
| TT-CAC/05 | Update check lists and tests | Based on CBS output. To be done |